## Settings
Settings and reference durations
Blue text on cream is an input. Everything else is a formula.
[7 empty] | Days off (holidays, leave) | One date per cell. Skipped by all date formulas.
Working hours per day (Lara) | 6 | Her average, from Lara.
Working days per week | 5 | Monday to Friday, confirmed.
Reference apartment area (m2) | 50 | Size the reference weeks apply to.
Idle working days between phases | 0 | Extra waiting time between any two phases. 0 = back to back.
Gantt first week (Monday) |  | Monday of the earliest project start. Overwrite with a date to pin the timeline.
Phase | Owner | Reference weeks | Scaling exponent | Ref. working days | Ref. hours | Why this scaling
Brief and concept | Anahit | 1 | 0 |  |  | Fixed. A conversation and a mood board take the same time at any size. Placeholder.
Floor planning | Lara | 1 | 0.5 |  |  | Layout effort follows room count and circulation problems, not area. Weak scaling.
3D modeling | Lara | 2 | 0.9 |  |  | Every surface gets modeled and materials assigned, so it tracks area closely.
Client approval | Anahit | 1 | 0 |  |  | Waiting on the client. Fixed. Placeholder.
Technical drawings | Lara | 1 | 0.8 |  |  | Sheet count follows rooms and wall and ceiling detail. Mostly area driven.
Furniture drawings | Lara | 2 | 0.7 |  |  | Driven by the number of custom pieces, which grows slower than area.
Procurement | Anahit | 3 | 0 |  |  | Ordering and lead times, mostly fixed. Placeholder.
Site supervision | Anahit | 6 | 0.5 |  |  | Longer for bigger sites but not in proportion. Placeholder.
Total
Ref. hours counts Lara's phases only. Lara's four phases total 6 weeks, 30 days, 180 hours at 50 m2.
How duration is calculated
Working days = ref. weeks x days per week x (area / ref. area) ^ exponent, then x complexity / share of Lara's time (Lara phases only).
Exponent 1.0 would be strictly linear. Below 1.0, a larger apartment takes less time per m2. 0 means fixed regardless of size.
The exponents are my design judgement, not measured data. Compare against 3 or 4 finished projects and adjust.
Complexity (Schedule sheet) is a per project multiplier: 1.0 normal, above 1.0 for heavy joinery or tricky layouts.
Share of Lara's time: 100% means the reference pace. Two parallel projects at 50% each run at half pace, so each takes twice as long.

## Schedule
Designature Studio project schedule
Fill the blue columns B to H and Notes. Each project has its own start date, so projects run in parallel. The Lara load row at the bottom shows when she is overbooked. Examples 01 to 06 are invented placeholders.
Weekly timeline, one column per week starting Monday
# | Project | Client | Area (m2) | Complexity | Share of Lara's time | Start | Status | Brief and concept days | start | end | Floor planning days | start | end | 3D modeling days | start | end | Client approval days | start | end | Technical drawings days | start | end | Furniture drawings days | start | end | Procurement days | start | end | Site supervision days | start | end | Finish | Lara hours | Notes
1 | Example 01 | Client A | 50 | 1 | 100% | 2026-10-05 | Active | [26 empty] | Reference size, Lara full time
2 | Example 02 | Client B | 72 | 1 | 50% | 2026-10-19 | Planned | [26 empty] | Parallel with 01 and 03, half her time
3 | Example 03 | Client C | 38 | 0.9 | 50% | 2026-10-26 | Planned | [26 empty] | Small, simple layout
4 | Example 04 | Client D | 95 | 1.2 | 100% | 2026-11-16 | Planned | [26 empty] | Lots of custom joinery
5 | Example 05 | Client E | 60 | 1 | 60% | 2026-12-07 | Planned
6 | Example 06 | Client F | 120 | 1.1 | 40% | 2027-01-11 | Planned | [26 empty] | House, runs in the background
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Lara load | Her phases only. Above 100% means overbooked.
Legend
Brief and concept
Floor planning
3D modeling
Client approval
Technical drawings
Furniture drawings
Procurement
Site supervision
Red header = current week. Grey and sand bars are Anahit's tracking phases. Lara load counts only phases whose Owner is Lara on the Settings sheet.