## Overview
Phase 1 Detailed Plan — Foundations (Weeks 1-2)
Objective: lock the brand and design-system foundations that every later phase builds on, while shipping the quick conversion fixes identified in the UI/UX audit. By the end of Phase 1, the logo is final, a v1 token-based component library is published, and five conversion fixes are live in production.
Workstream summary
Workstream | Total Tasks | P0 Tasks | Done | % Complete
Brand | 5 | 2 | 0 | 0%
Design System | 6 | 4 | 3 | 50%
Messaging & CTA | 20 | 9 | 0 | 0%
Pricing & Credits | 3 | 2 | 0 | 0%
Wrap-up | 2 | 1 | 0 | 0%
Total | 36 | 18 | 3 | 8.333%
Priority summary
Priority | Task Count | Done
P0 - Critical | 18 | 2
P1 - High | 11 | 1
P2 - Medium | 7 | 0
Phase 1 exit criteria (definition of done)
- Final logo, favicon, and icon set are locked and in use across the site.
- v1 token-based component library is published and used for every new UI shipped in this phase.
- Homepage hero states the AI+human hybrid model live in production.
- "Try AI Free" nav pill is live on every legacy page.
- A single, standardized "Ask a Designer" CTA replaces the five prior phrasings everywhere.
- Credit-consumption audit memo is delivered to stakeholders ahead of Phase 3.
- Non-blocking persona row is live on the homepage.
- Redesign My Room results screen shows one primary CTA instead of four.
- Score My Room gating matches the "Free - 3/mo" pattern used by the other live tools.

## Phase 1 Tasks
ID | Workstream | Feature | Task | Priority | Owner | Week | Start Day | End Day | Duration (days) | Depends On | Deliverable / Acceptance Criteria | Status
BR1 | Brand | Logo finalization | Review existing logo variations and gather stakeholder feedback | P0 - Critical | Brand Designer | Week 1 | 1 | 1 | 1 | - | Signed-off direction memo from stakeholders | In Progress
BR2 | Brand | Logo finalization | Finalize primary mark and wordmark lockup | P0 - Critical | Brand Designer | Week 1 | 1 | 2 | 2 | BR1 | Final vector logo files (SVG/AI) approved | In Progress
BR3 | Brand | Logo finalization | Define color variants (light / dark / mono) | P1 - High | Brand Designer | Week 1 | 2 | 2 | 1 | BR2 | 3 approved color variants exported | Not Started
BR4 | Brand | Logo finalization | Export favicon and app icon set | P1 - High | Brand Designer | Week 1 | 2 | 2 | 1 | BR2 | Favicon .ico + app icons (16-512px) delivered | Not Started
BR5 | Brand | Logo finalization | Document logo usage guidelines | P2 - Medium | Brand Designer | Week 1 | 2 | 2 | 1 | BR2 | 1-page usage doc: clear space, minimum size, do/don't | Not Started
DS1 | Design System | Token library | Audit current site for existing visual patterns | P0 - Critical | Product Designer | Week 1 | 1 | 2 | 2 | - | Pattern inventory doc covering colors, type, spacing, components | Done
DS2 | Design System | Token library | Define token taxonomy (color, type, spacing, radius, shadow) | P0 - Critical | Design Lead | Week 1 | 2 | 3 | 2 | DS1 | Token naming spec reviewed and approved | Done
DS3 | Design System | Token library | Set up base Figma library file structure | P1 - High | Product Designer | Week 1 | 3 | 3 | 1 | DS2 | Library file created with page structure in place | Done
DS4 | Design System | Token library | Populate core tokens (color / type / spacing) into library | P0 - Critical | Product Designer | Week 1 | 3 | 4 | 2 | DS3 | All core tokens published as Figma variables | In Progress
DS5 | Design System | Token library | Build enhanced core components (buttons, cards, badges, fields) | P0 - Critical | Product Designer | Week 2 | 6 | 8 | 3 | DS4 | Component set covers every pattern used in this phase's CTA work | In Progress
DS6 | Design System | Token library | QA library against live site and publish v1 | P1 - High | Design Lead | Week 2 | 8 | 9 | 2 | DS5 | v1 library published; no orphaned styles; changelog written | In Progress
CX1 | Messaging & CTA | Hero messaging | Draft 3 hero headline / sub-line variants (AI+human hybrid) | P0 - Critical | Copywriter | Week 1 | 1 | 1 | 1 | - | 3 options delivered with rationale | Not Started
CX2 | Messaging & CTA | Hero messaging | Stakeholder review and final copy sign-off | P1 - High | PM | Week 1 | 1 | 2 | 2 | CX1 | Final copy approved in writing | Not Started
CX3 | Messaging & CTA | Hero messaging | Implement new hero copy on homepage | P0 - Critical | Frontend Engineer | Week 1 | 2 | 2 | 1 | CX2 | Live on staging, matches approved copy exactly | Not Started
CX4 | Messaging & CTA | Hero messaging | QA hero across breakpoints | P2 - Medium | QA | Week 1 | 2 | 2 | 1 | CX3 | No layout breaks on mobile, tablet, or desktop | Not Started
CX5 | Messaging & CTA | Nav CTA pill | Spec "Try AI Free" nav pill component | P1 - High | Product Designer | Week 1 | 1 | 1 | 1 | - | Component spec ready (states, sizing, placement) | Not Started
CX6 | Messaging & CTA | Nav CTA pill | Implement pill across every legacy page | P0 - Critical | Frontend Engineer | Week 1 | 2 | 3 | 2 | CX5 | Pill live on Home, Services, Portfolio, About nav | Not Started
CX7 | Messaging & CTA | Nav CTA pill | QA nav links and mobile menu collapse | P2 - Medium | QA | Week 1 | 3 | 3 | 1 | CX6 | No broken links; mobile menu unaffected | Not Started
CX8 | Messaging & CTA | Escalation CTA | Decide on single escalation CTA name and framing | P0 - Critical | PM | Week 1 | 1 | 1 | 1 | - | Name + microcopy approved (e.g. "Ask a Designer") | Not Started
CX9 | Messaging & CTA | Escalation CTA | Audit all current instances of the escalation CTA | P1 - High | Product Designer | Week 1 | 1 | 1 | 1 | - | Inventory of every current instance and page | Not Started
CX10 | Messaging & CTA | Escalation CTA | Update copy and styling at every instance | P0 - Critical | Frontend Engineer | Week 1 | 3 | 4 | 2 | CX8, CX9 | All instances use the identical name and visual style | Not Started
CX11 | Messaging & CTA | Escalation CTA | QA consistency pass site-wide | P2 - Medium | QA | Week 1 | 4 | 4 | 1 | CX10 | Zero mismatched CTA labels found | Not Started
CX12 | Messaging & CTA | Persona row | Design non-blocking persona row UI (2 buttons) | P1 - High | Product Designer | Week 2 | 6 | 6 | 1 | DS4 | Two-button row spec using library components | Not Started
CX13 | Messaging & CTA | Persona row | Implement persona row and routing logic | P0 - Critical | Frontend Engineer | Week 2 | 7 | 8 | 2 | CX12 | Live on staging; correctly reorders tool teaser per choice | Not Started
CX14 | Messaging & CTA | Persona row | QA persona row on mobile and desktop | P2 - Medium | QA | Week 2 | 8 | 8 | 1 | CX13 | Both persona paths tested; no dead ends | Not Started
CX15 | Messaging & CTA | Results screen CTA | Define new CTA hierarchy (1 primary + collapsed next steps) | P0 - Critical | Product Designer | Week 2 | 6 | 6 | 1 | - | Wireframe approved by PM and design lead | Not Started
CX16 | Messaging & CTA | Results screen CTA | Implement CTA hierarchy change | P0 - Critical | Frontend Engineer | Week 2 | 7 | 7 | 1 | CX15 | Live on staging, matching the approved wireframe | Not Started
CX17 | Messaging & CTA | Results screen CTA | QA and verify analytics events still fire correctly | P2 - Medium | QA | Week 2 | 8 | 8 | 1 | CX16 | All 4 original CTA events still tracked correctly | Not Started
CX18 | Messaging & CTA | Score My Room gating | Update gating logic to "Free - 3/mo" | P0 - Critical | Backend Engineer | Week 2 | 8 | 9 | 2 | PR2 | Cap enforced server-side, matching the other two live tools | Not Started
CX19 | Messaging & CTA | Score My Room gating | Update UI copy to reflect the new free cap | P1 - High | Frontend Engineer | Week 2 | 9 | 9 | 1 | CX18 | UI shows "Free - 3/mo" consistent with other tools | Not Started
CX20 | Messaging & CTA | Score My Room gating | QA credit counter and cap behavior | P1 - High | QA | Week 2 | 9 | 9 | 1 | CX18 | Counter decrements correctly and resets monthly | Not Started
PR1 | Pricing & Credits | Credit audit | Pull current credit costs per tool step | P0 - Critical | Backend Engineer | Week 2 | 6 | 6 | 1 | - | Raw cost data exported per tool and step | Not Started
PR2 | Pricing & Credits | Credit audit | Map costs against advertised free caps | P0 - Critical | PM/Analyst | Week 2 | 6 | 7 | 2 | PR1 | Comparison table: advertised vs. actual cost per step | Not Started
PR3 | Pricing & Credits | Credit audit | Write findings memo and flag discrepancies | P1 - High | PM | Week 2 | 7 | 7 | 1 | PR2 | Memo shared with stakeholders ahead of Phase 3 pricing work | Not Started
WU1 | Wrap-up | Phase close | Phase 1 review, demo, and sign-off | P0 - Critical | PM | Week 2 | 10 | 10 | 1 | ALL | Every P0 task done; stakeholders sign off | Not Started
WU2 | Wrap-up | Phase close | Phase 1 retro and Phase 2 kickoff prep | P2 - Medium | PM | Week 2 | 10 | 10 | 1 | WU1 | Retro notes and Phase 2 kickoff agenda sent | Not Started

## Gantt (Day 1-10)
ID | Task | Workstream | Day 1 Mon | Day 2 Tue | Day 3 Wed | Day 4 Thu | Day 5 Fri | Day 6 Mon | Day 7 Tue | Day 8 Wed | Day 9 Thu | Day 10 Fri
BR1 | Review existing logo variations and gather stakeholder feedback | Brand
BR2 | Finalize primary mark and wordmark lockup | Brand
BR3 | Define color variants (light / dark / mono) | Brand
BR4 | Export favicon and app icon set | Brand
BR5 | Document logo usage guidelines | Brand
DS1 | Audit current site for existing visual patterns | Design System
DS2 | Define token taxonomy (color, type, spacing, radius, shadow) | Design System
DS3 | Set up base Figma library file structure | Design System
DS4 | Populate core tokens (color / type / spacing) into library | Design System
DS5 | Build enhanced core components (buttons, cards, badges, fields) | Design System
DS6 | QA library against live site and publish v1 | Design System
CX1 | Draft 3 hero headline / sub-line variants (AI+human hybrid) | Messaging & CTA
CX2 | Stakeholder review and final copy sign-off | Messaging & CTA
CX3 | Implement new hero copy on homepage | Messaging & CTA
CX4 | QA hero across breakpoints | Messaging & CTA
CX5 | Spec "Try AI Free" nav pill component | Messaging & CTA
CX6 | Implement pill across every legacy page | Messaging & CTA
CX7 | QA nav links and mobile menu collapse | Messaging & CTA
CX8 | Decide on single escalation CTA name and framing | Messaging & CTA
CX9 | Audit all current instances of the escalation CTA | Messaging & CTA
CX10 | Update copy and styling at every instance | Messaging & CTA
CX11 | QA consistency pass site-wide | Messaging & CTA
CX12 | Design non-blocking persona row UI (2 buttons) | Messaging & CTA
CX13 | Implement persona row and routing logic | Messaging & CTA
CX14 | QA persona row on mobile and desktop | Messaging & CTA
CX15 | Define new CTA hierarchy (1 primary + collapsed next steps) | Messaging & CTA
CX16 | Implement CTA hierarchy change | Messaging & CTA
CX17 | QA and verify analytics events still fire correctly | Messaging & CTA
CX18 | Update gating logic to "Free - 3/mo" | Messaging & CTA
CX19 | Update UI copy to reflect the new free cap | Messaging & CTA
CX20 | QA credit counter and cap behavior | Messaging & CTA
PR1 | Pull current credit costs per tool step | Pricing & Credits
PR2 | Map costs against advertised free caps | Pricing & Credits
PR3 | Write findings memo and flag discrepancies | Pricing & Credits
WU1 | Phase 1 review, demo, and sign-off | Wrap-up
WU2 | Phase 1 retro and Phase 2 kickoff prep | Wrap-up

## Legend
Legend
Priority
P0 - Critical | Must ship this phase. Blocks the phase exit criteria or a downstream phase.
P1 - High | Should ship this phase. Important but has limited workaround if slipped by a few days.
P2 - Medium | Nice to have this phase. Safe to slip into Phase 2 if the schedule is tight.
Workstream
Brand
Design System
Messaging & CTA
Pricing & Credits
Wrap-up
How to use this workbook
- Phase 1 Tasks is the working sheet — update Owner, Status, and dates as work progresses.
- Priority, Owner, Workstream, and Status are all dropdowns; colors update automatically.
- Depends On lists task IDs that must finish first — check it before moving a task's dates.
- The Gantt tab is a snapshot of this plan; if dates shift, edit Start/End Day on Phase 1 Tasks and rebuild the shading.
- The Overview tab's totals and % complete update automatically as Status is marked "Done".